## Prelim (hidden)
KERJA-KERJA PEMBAIKAN FIRE COMMAND CENTRE (FCC) DI KAMPUS UNIVERSITI TEKNOLOGI MALAYSIA, JOHOR BAHRU, JOHOR
PART A1 - PRELIMINARIES AND GENERAL CONDITIONS
ITEM | DESCRIPTION | [5 empty] | UNIT | QUANTITY | RATE (RM) | AMOUNT (RM)
Project Signboard
A | The Contractor shall provide, erect, and maintain a project signboard as specified.
Site Survey And Setting Out
B | The Contractor shall employ a licensed surveyor to carry out site surveys before commencement and setting out of the Works.
Temporary Diversion And Relocation Of Existing Overhead And Underground Services
C | The Contractor shall enquire from the various authorities and make arrangements for the disconnection, removal, relocation and reconnection of services and pay all necessary cost and fees in connection therewith and make good all damage as specified.
Construction Plan
D | The Contractor shall submit to the S.O. for his approval the following as specified a) Programme of Works b) Method statements c) Contractor's organisation chart d) Schedules e) Quality Assurance Plan for Works Contract worth RMIO Million and above.
i) Provide a quality Assurance Team full time on Site for the institution, administration and maintenance of the Quality Assurance Plan and the preparation and submission of all Quality Assurance Reports as specified, throughout the duration of the contract.
ii) The Contractor shall appoint a suitably qualified and experienced person to act solely as a Quality Assurance Officer full time on site to lead Quality Assurance Team. (Refer Addendum to specification for project worth RM 10 Million and above).
Contractor's Plant
E | The Contractor shall provide, erect, keep insured, maintain and remove on completion all requisite scaffolding, hoist, cranage, construction plant, ladder, staging, tarpaulins, et cetera (excluding piling and pile testing equipment), as necessary for the execution of the Works.
Temporary Water And Power Supplies For The Works
F | The Contractor shall provide adequate power and water supplies for the execution of the works including paying all associated costs and fees as specified.
| TO COLLECTION | [8 empty] | 0
TO COLLECTION
The following abbreviations appearing in these Specifications have their meanings as assigned against them:
| i) | B.Q. | - | Bills of Quantities
| ii) | CIAST | - | Pusat Latihan Pengajar dan Kemahiran Lanjutan
| iii) | CIDB | - | Construction Industry Development Board
| iv) | CoW | - | CoW
| v) | DGFR | - | Director General of Fire and Rescue
| vi) | DOE | - | Department of Environment
| vii) | DOSH | - | Department of Occupational Safety and Health
| viii) | EMP | - | Environmental Management Plan
| ix) | JKR | - | Jabatan Kerja Raya
| x) | MOH | - | Ministry of Health
| xi) | MSMA | - | Manual Saliran Mesra Alam
| xii) | MTIB | - | Malaysian Timber Industry Board
| xiii) | PDRM | - | Polis Diraja Malaysia
| xiv) | P.E | - | Professional Engineer
| xv) | R.O.W | - | Right Of Way
| xvi) | S.O. | - | Superintending Officer
| xvii) | S.P. | - | System Provider
| xviii) | SIRIM | - | Standards and Industrial Research Institute of Malaysia
| xix) | SPAN | - | Suruhanjaya Perkhidmatan Air Negara
All Standards referred to in this Specification together with any addenda issued shall be deemed to be the editions current at the time of Tender. If the Malaysian Standard (MS) exists, which the S.O. deems to be equivalent to the British or other Standard specified, then the MS shall be followed. Other equivalent standards specifying superior material may be used with the approval of the S.O.
In the event of any discrepancy between the provision of this Specification and the provision within the relevant Standards or Codes of Practice (CP) as mentioned in this Specification, then the provision of this Specification shall take precedence.
TO COLLECTION
Standard (Cont'd)
The following references shall mean:
|  | AASHTO |  | - | The American Association of State Highway and Transportation Officials
|  | ANSI |  | - | American National Standards Institute
|  | API |  | - | American Petroleum Institute Specification
|  | AS/NZS |  | - | Australian/New Zealand Standard
|  | ASTM |  | - | The American Society for Testing and Materials
|  | AWWA |  | - | American Water Works Association
|  | BS |  | - | British Standards Specification as issued by the British Standards House, London (the latest amendment) China National Standard
|  | CNS |  | - | British Standard Code of Practice issued by the Council for
|  | CP |  | - | Code of Practice in Great Britain (the latest amendment) German Institute for Standardisation
|  | DIN |  | - | German Institute for Standardisation
|  | EN |  | - | European Standard which is a standard that has been adopted by one of the three recognized European Standardisation Organisations (ESOs), that is CEN (European Committee for Standardization), CENELEC (European Committee for Electrotechnical Standardisation) and ETSI (European Telecommunications Standards Institute)
|  | JIS |  | - | Japanese Industrial Standard
|  | MS |  | - | Malaysian Standards as issued by the Standards and Industrial Research Institute of Malaysia (the latest amendment)
The Contract Documents shall consist of :-
| i) | PWD Form of Contract (for contract based on Drawings and Specification or for contract based on Quantities);
| ii) | Form of Tender;
| iii) | Letter of Acceptance of Tender;
| iv) | Special Provisions to the Conditions of Contract as listed in the PWD Form of Contract;
| v) | Contract Drawings;
| vi) | Specifications;
TO COLLECTION
Contract Document (Cont'd)
| vii) | Summary of Tender (for contract based on Quantities, this item is part of the B.Q.);
| viii) | Schedule of Rates (for contract based on Drawings and Specifications) or B.Q. (for contract based on Quantities);
| ix) | Any other relevant documents included therein.
The documents shall be taken as mutually explanatory of each other and in case of any discrepancy or inconsistency, the following rules shall apply:
| i) | The Conditions of Contract (PWD Form 203/ PWD Form 203A) shall take preference over all other documents.
| ii) | Special Provisions to Conditions of Contract shall take preference over Conditions of Contract.
| iii) | In Drawings, large scale details shall take preference over small scale Drawings.
| iv) | The Addendum Specification shall take preference over the Standard Specifications and Drawings.
| v) | Drawings shall take preference over Standard Specifications.
Any discrepancies shall be referred as soon as possible to the S.O. who shall decide which shall be followed.
The Contractor shall take proper measure of adjoining property and shall comply with the requirements imposed by the S.O at his own expense.
During construction, the contractor shall across any cables, pipe, et cetera, he shall immediately stop work and refer to the S.O for further instructions and make arrangements for the disconnection, et cetera. The contractor shall be responsible for making good all damage to the cable, et cetera and shall indemnify the UTM against any claims as a result of such damage.
Materials and workmanship throughout the Works shall be in accordance with the Drawings and Specifications and to the approval of the S.O.
Where required, all works shall be executed by competent and skilled workers in the related field.
Wherever in this Specification any proprietary goods or materials are specified, goods or materials of alternative manufacture may be considered for acceptance provided they comply in all respect as regards to appearance and quality, and are approved by the S.O.
TO COLLECTION
Goods, Materials And Workmanship (Cont'd)
If, however, the Contractor has shown beyond reasonable doubt that the specified goods or materials cannot be obtained and the S.O. is satisfied with regard to the non-availability of the goods and materials, the benefit of cost savings, if any, resulting from the Contractor’s proposal or substitution of goods or materials approved by the S.O., shall be deducted from the Contract Sum.
The Contractor shall use locally manufactured materials and goods whichever is relevant. If the Contractor fails to comply with this requirement, a penalty shall be imposed and/or the materials supplied shall be rejected.
The locally manufactured materials and goods which are not listed aforesaid, may be permitted if the materials have been tested and certified by IKRAM QA Services Sdn. Bhd. or SIRIM QA Services Sdn. Bhd. whichever is relevant. If the testing cannot be carried out by IKRAM QA Services Sdn. Bhd. or SIRIM QA Services Sdn. Bhd., the Contractor may apply and, subject to the approval of the S.O., carry out the testing by other agencies.
Under no circumstances will the Contractor be permitted to incorporate or supply imported materials, plant, equipment, or other goods into the Works or forming part of the scope of the Works except those approved by the Government, prior to the execution of the Contract. The Contractor shall substitute any materials, plant, equipment, or other goods proposed to be imported but not approved by the Government, with suitable local materials, plant, equipment, or other goods, including making any necessary sub-sequential changes or adjustments to the design of the Works to accommodate such substitution, all to the concurrence of the S.O.
The Contractor shall ensure that the procurement of approved imported materials, plant, equipment, or other goods are obtained directly from the country of origin based on Free On Board (F.O.B) or other similar basis. The transportation and insurance of such imported materials, plant, equipment, or other goods from the country of origin to the Site shall be arranged by the Contractor through approved Government’s Multi Modal Transport Operators (MTO). The Contractor shall allow in his tender all costs and time required in complying with the requirements of this clause including the cost required for the services provided by the MTO.
The Contractor shall submit documentary evidence of compliance with this clause to the S.O. within one (1) month from the date of each delivery to the Site of such materials, plant, equipment, vehicles or other goods.
TO COLLECTION
Notwithstanding the materials and products shown on the Drawings or specified herewith, the Contractor is encouraged to propose, at no additional cost, alternative equivalent materials or “Green” products to be used in the Works, subject to the approval of the S.O., such as:
| i) | Environmentally friendly materials or “Green” products that are certified under the Global Eco-Label Network (GEN) certification.
| ii) | Products self-declared “Green” by the manufacturer with certification from recognised independent certifying bodies and not a member of GEN.
Unless otherwise specified hereinafter or shown on the Drawings, only materials of metric dimension shall be used for the Works. Materials of equivalent imperial dimension may only be used if the Contractor can satisfy the S.O. that the required materials are not available in metric dimension.
The Contractor shall place his orders for specified materials at the earliest possible date after notification of acceptance of tender or at such times as may be specifically stated for any particular material.
The Contractor shall submit for approval relevant shop drawings as requested by the S.O.
The Contractor shall submit samples of materials or execute samples of workmanship for the S.O.’s approval, and for further samples as required until the samples submitted or executed are in accordance with this Specification.
The Contractor shall prepare sample installations as required to match specified works in all respects before proceeding with work. Mock-up units approved and accepted by the S.O. shall be referred as the Standard of comparison for the work.
The Contractor shall submit for approval as requested by the S.O., manufacturer's specifications, installation instruction, general recommendation for the work, including certified laboratory test reports and other data required to show compliance with these specifications.
TO COLLECTION
The Contractor shall provide, erect, keep insured, maintain and remove on completion all requisite scaffolding, hoist, ladder, staging, tarpaulins, tools, vehicles, tackles and other plants and apparatus (excluding piling and pile testing equipment), as required by all trades as are necessary for the execution of the Works.
All mechanical plant used by the Contractor shall be of such type, size and capacity suitable to the type and nature of the Works and site conditions where the Works are to be executed.
The Contractor shall take note the required cranage for the erection and completion of precast components and to ensure that the said cranes are or will be available during the construction stages.
Within fourteen (14) days after the receipt of the Letter of Acceptance, the Contractor shall submit to the S.O. for his approval the following:
| i) | Programme of Works
A detailed work programme using the Critical Path Method (CPM) including electronic and printed copies of all data. The programme shall be presented in the form of Gantt chart and network diagrams indicating, among others the critical activities, interface dates and resources required to complete the works within the Contract period. The Contractor shall be required to update all information and maintain the planned programme weekly/monthly using the CPM or as instructed by the S.O.
The work programme shall be prepared and maintained by trained and qualified personnel.
| ii) | Method statements
The Contractor shall also furnish in writing to the S.O. or S.O’s Representatives particulars of the Contractor’s method statements for carrying out such works and of the construction plant and temporary works, if any, which the Contractor intends to supply, use or construct as the case may be. The submission to and approval by the S.O. or the S.O.’s Representatives of such programme or the furnishing of such particulars shall not relieve the Contractor of any of his duties or responsibilities under the Contract.
TO COLLECTION
Construction Plan (Cont'd)
If at any time it should appear to the S.O that the actual progress of the Works does not conform to the approved programme the Contractor shall submit for approval, a revised programme showing the modifications to the previously approved programme and additional resources necessary to ensure the comp
Site Security
A | The Contractor shall provide all necessary personnel and lighting for the security of the site at all times until completion of the whole Works as specified
Temporary Access And Maintenance Of Existing Roads
B | The Contractor shall provide and maintain all necessary temporary roads, culverts, tracks, bridges, et cetera for access to and within the Site as specified
C | The Contractor shall maintain all access including existing roads, bridges, drains, culverts, roadside furniture, and all other appurtenances and services on such roads throughout the construction period. The Contractor shall make good any above mentioned item damaged by any work carried out by him.
D | The Contractor shall locate the actual position and provide support and full protection of existing services and mains during the progress of the Works. The Contractor shall inform the S.O. of all arrangements with the various authorities.
Control Of Workmen, Plant And Machinery At Site
E | The Contractor shall ensure the safety, health and welfare at work of all his workmen as specified.
Contractor's Temporary Accommodation And Facilities For Workmen Living On Site
F | The Contractor shall provide and maintain all temporary accommodation and facilities including temporary lighting, plumbing, water storage, sanitary and sewerage for his labour and staff living on Site as specified.
Contractor's Office And Storage
G | The Contractor shall provide and maintain Contractor's office and storage on the Site in positions as approved by the S.O. and as specified,
Care And Protection Of Materials And Works
H | The Contractor shall provide and maintain everything necessary for proper protection of materials and Works from any damage by weather.
Shop Drawings, Samples And Mock-ups
J | The Contractor shall submit relevant shop drawings, samples of materials or workmanship and mock-ups units as specified for the S.O. 's approval.
| TO COLLECTION | [8 empty] | 0
Progress Photographs
A | The Contractor shall take progress photographs and submit to the S.O. as specified.
Material Testing Laboratory And Staff
B | The Contractor shall provide/erect a testing laboratory within the site or rent a premise or propose an accredited laboratory approved by SIRIM as specified. The Laboratory shall be equipped with the necessary equipment and staff required to carry out the tests as identified in APPENDIX A/4 (List of Laboratory Equipment).
Office Accommodation For S.O.
C | The Contractor shall provide and maintain a site office or relocatable site office or rent a premise for the use of the JKR supervisory staff which shall meet the requirement of the JKR design as specified.
Telephone For S.O.
D | The Contractor shall provide a permanent telephone at the SO.'s site office for the sole use of the S.O. and his representatives as specified.
Survey Instruments And Personnel
E | The Contractor shall provide all such instruments, equipment and survey personnel as specified throughout the duration of the original Contract Period until 6 months after the issuance of the Certificate of Practical completion as per SO required.
Site Items For S.O./Office Equipment And Facilities
F | The Contractor shall provide all Personal Protective Equipment required for the use of the S.O. and his supervisory staff complete as specified and complying with DOSH requirements.
G | The Contractor shall provide suitable types of fire extinguishers as specified.
H | The Contractor shall provide the equipment and facilities as listed as specified in APPENDIX A/2 for the use of the S.O., his representatives and staff throughout the duration of the original Contract Period.
J | The Contractor shall provide suitable transportation service by means of vehicle(s) including licensed and competent driver(s) as specified in APPENDIX A/3 throughout the duration of the original Contract Period.
| TO COLLECTION | [8 empty] | 0
| TO COLLECTION | [8 empty] | #REF!
Progress Photographs
A | The Contractor shall take progress photographs and submit to the S.O. as specified.
Material Testing Laboratory And Staff
B | The Contractor shall provide/erect a testing laboratory within the site or rent a premise or propose an accredited laboratory approved by SIRIM as specified. The Laboratory shall be equipped with the necessary equipment and staff required to carry out the tests as identified in APPENDIX A/4 (List of Laboratory Equipment).
Office Accommodation For S.O.
C | The Contractor shall provide and maintain a site office or relocatable site office or rent a premise for the use of the JKR supervisory staff which shall meet the requirement of the JKR design as specified.
Telephone For S.O.
D | The Contractor shall provide a permanent telephone at the SO.'s site office for the sole use of the S.O. and his representatives as specified.
Survey Instruments And Personnel
E | The Contractor shall provide all such instruments, equipment and survey personnel as specified throughout the duration of the original Contract Period until 6 months after the issuance of the Certificate of Practical completion as per SO required.
Site Items For S.O./Office Equipment And Facilities
F | The Contractor shall provide all Personal Protective Equipment required for the use of the S.O. and his supervisory staff complete as specified and complying with DOSH requirements.
G | The Contractor shall provide suitable types of fire extinguishers as specified.
H | The Contractor shall provide the equipment and facilities as listed as specified in APPENDIX A/2 for the use of the S.O., his representatives and staff throughout the duration of the original Contract Period.
J | The Contractor shall provide suitable transportation service by means of vehicle(s) including licensed and competent driver(s) as specified in APPENDIX A/3 throughout the duration of the original Contract Period.
TO COLLECTION
Safe Working Area
A | The Contractor shall supply, erect, maintain and remove on completion of the Works, scaffolding and working platform with safety nettings, catch platforms, safety barricades, fencing, railing, screen wire netting and toe board, guardrails or board fences and sufficient illuminations, all as specified.
B | The Contractor shall supply, erect, maintain and remove on completion of the Works, adequate, protective and security hoarding, scaffolding and working platform with safety nettings and such other safety measures necessary to ensure the safety of the workers, personnel, public and others at or within the vicinity of the Site, all as specified.
Safety, Health And Welfare
C | The Contractor shall ensure the safety, health and welfare at work site as specified including but not limited to : a) Provision of First Aid Kit b) Pest control including keeping the site clean and dry to prevent breeding of mosquitoes, rodents, insects and vermin of any kind. c) Fogging at regular intervals
D | *The Contractor shall employ a Safety and Health Officer (SHO) registered with DOSH for the entire contract period to be stationed fulltime at the site (for works exceeding RM 20 million contract value. Delete if not applicable
E | The Contractor shall employ a Site Safety Supervisor (SSS) registered with DOSH to be stationed a minimum of 15 hours a week at the site for the entire duration of the construction period.
F | The Contractor shall submit 5 copies of Safety and Health Plan (S-Plan) as required in APPENDIX A/5 as specified.
G | The Contractor shall submit 5 copies of monthly Safety and Health Report as required in APPENDIX A/6 as specified.
H | The Contractor shall provide and maintain adequate traffic safety and control including signages, warning lights and flagmen as necessary.
Keeping The Site Tidy
J | The Contractor shall make every effort to keep the Site in a reasonably clean and tidy condition for the duration of the Works as specified.
TO COLLECTION
Coordination Of Mechanical And Electrical (M & E) Services
A | The Contractor shall be responsible for coordinating the implementation of all M & E works as specified and appoint M&E Services Coordinator based on project cost as follows.
|  |  | Project Cost (RM) |  |  | Minimum Requirement Of M & E Coordinator
|  |  | between 10 to 50 million |  |  | 1 Engineer& 1 COW
|  |  | more than 50 million |  |  | 1 Engineer&2 COW
As-built Drawings
B | The Contractor shall provide four (4) sets of the approved As-built drawings after completion of each section of the Works in the form as specified.
Clearing, Cleaning And Making Good On Completion
C | The Contractor shall clear and clean the Works including existing roads, drains bounding the Site of any debris, earth, et cetera, and make good all damages upon completion as specified.
Form of Contract
D | The Contractor shall refer to the Standard Form of Contract for further information. The Contractor may price here for all the expenses involved in complying with the terms of these Clauses, otherwise such expenses are deemed to be included elsewhere.
Clause 13
E | Performance Bond
For due observance and performance of this contract the Contractor shall have to provide:
Performance Bond in the form of an approved Bank or Insurance Guarantee equal to five percent (5%) of the contract sum to be deposited with the Government as a condition precedent to the commencement of any work under this contract.
Clause 15
F | Insurance Against Personal Injuries And Damage To Property
Clause 16
G | Indemnities to Government in Respect of Claim by Workmen
Clause 17
H | Employee's Social Security Act, 1969
Clause 178
J | Insurance of Works.
TO COLLECTION
Form of Contract (cont'd)
Clause 22
A | Design, Sub-clause 22.2 Design Guarantee Bond
Clause 35
B | Materials, goods and workmanship Opening up of work for inspection or testing of materials or goods
Clause 59 Site Aqent And Assistants
C | The Contractor shall keep constantly on the Site for the full duration of the Contract a competent, efficient, suitably qualified, experienced and good character Site Agent and his assistants in each trade as may be necessary, who must be capable of receiving instructions in Bahasa Malaysia, and in default it shall be the responsibility of the Contractor to provide replacement for them and all wages and other expenses in connection with the employment of such replacement site agent and assistants. Any directions, explanations or instructions given to such site agent by the S.O. shall be deemed to have been given to the Contractor under this contract. provide all necessary superintending order
TO COLLECTION
COLLECTION :
From Page No. PHT/A/1
From Page No. PHT/A/2
From Page No. PHT/A/3
From Page No. PHT/A/4
From Page No. PHT/A/5
From Page No. PHT/A/6
From Page No. PHT/A/7
| CARRIED FORWARD TO GENERAL SUMMARY (RHT/1) | [8 empty] | 0

## Sheet1 (hidden)
KERJA-KERJA PEMBAIKAN FIRE COMMAND CENTRE (FCC) DI KAMPUS UNIVERSITI TEKNOLOGI MALAYSIA, JOHOR BAHRU, JOHOR
PRELIMINARIES
ITEM | DESCRIPTION | AMOUNT (RM)
PRELIMINARIES ITEM
The Preliminary items as set out hereunder are deemed to apply to the whole of the works all as shown on the drawings and/or described in this Bills of Quantities and the Contractor shall allow for complying with same and for any cost incurred in connection therewith. The Contractor shall note that any clause or item listed in this section which has not been priced, it shall be deemed that the cost of such clause or items has been included elsewhere in this section or in the Bills of Quantities section and those unpriced clause or items shall be borned by Contractor.
A | Shop Drawings, Samples And Mock-ups
The Contractor shall submit for approval relevant shop drawings as requested by the S.O.
The Contractor shall submit samples of materials or execute samples of workmanship for the S.O.’s approval, and for further samples as required until the samples submitted or executed are in accordance with this Specification.
The Contractor shall prepare sample installations as required to match specified works in all respects before proceeding with work. Mock-up units approved and accepted by the S.O. shall be referred as the standard of comparison for the work.
The Contractor shall submit for approval as requested by the S.O., manufacturer's specifications, installation instruction, general recommendation for the work, including certified laboratory test reports and other data required to show compliance with these specifications.
B | Contractor's Plant
The Contractor shall provide, erect, keep insured, maintain and remove on completion all requisite scaffolding, hoist, cranage, construction plant, ladder, staging, tarpaulins, et cetera (excluding piling and pile testing equipment), as necessary for the execution of the Works.
C | Construction Plan
The Contractor shall submit to the S.O. for his approval the following as specified a) Programme of Works b) Method statements c) Contractor's organisation chart d) Schedules e) Quality Assurance Plan for Works Contract worth RMIO Million and above.
i) Provide a quality Assurance Team full time on Site for the institution, administration and maintenance of the Quality Assurance Plan and the preparation and submission of all Quality Assurance Reports as specified, throughout the duration of the contract.
ii) The Contractor shall appoint a suitably qualified and experienced person to act solely as a Quality Assurance Officer full time on site to lead Quality Assurance Team. (Refer Addendum to specification for project worth RM 10 Million and above).
TO COLLECTION
PRELIMINARIES ITEM (Cont'd)
A | Project Signboard
Provide a new project signboard in Bahasa Melayu as per UTM’s drawing and approved by S.O. Adapt, extend, sign write from time to time as required by the S.O. within one (1) month after received Letter of Acceptance and pay all costs in connection for the duration of the contract period.
B | Progress Photographs
The Contractor shall prepare and submit to the S.O. within first week of every month four (4) copies of report on the progress of works at site. The report shall be by Section and/or Trades and to include the works of Sub-Contractors. It should also stated the number and deployment of workmen employed, materials and goods delivered, extent and type of plant used, site instruction, weather conditions, OSHE reports as required by the OSHA, visitors and other information relevant to the Works. The Contractor shall take progress photographs of the works at monthly interval as directed by the S.O. The average number of different photographs to be taken shall be sufficient enough to show the progress of the work but in any case the average number per month shall not be less than four (4) postcard size coloured prints and each of the approved photographs submitted to the S.O all titled and dated.
C | Temporary Access And Maintenance Of Existing Roads
The Contractor shall provide and maintain all necessary temporary roads, culverts, tracks, bridges, et cetera for access to and within the Site as specified.
The Contractor shall maintain all access including existing roads, bridges, drains, culverts, roadside furniture, and all other appurtenances and services on such roads throughout the construction period. The Contractor shall make good any above mentioned item damaged by any work carried out by him.
The Contractor shall locate the actual position and provide support and full protection of existing services and mains during the progress of the Works. The Contractor shall inform the S.O. of all arrangements with the various authorities.
D | Temporary Diversion And Relocation Of Existing Overhead And Underground Services
The Contractor shall enquire from the various authorities and make arrangements for the disconnection, removal, relocation and reconnection of services and pay all necessary cost and fees in connection therewith and make good all damage as specified.
E | Temporary Water And Power Supplies For The Works
Temporary water and electrical supply obtained from UTM shall be approved and billed accordingly by the S.O. The Contractor to liaise with the UTM to take possession of and install all meters and connect all services including dismantling all temporary services upon completion.
TO COLLECTION
PRELIMINARIES ITEM (Cont'd)
A | Site Security
The Contractor shall provide all necessary personnel and lighting for the security of the site at all times until completion of the whole Works as specified
B | Care And Protection Of Materials And Works
The Contractor shall provide and maintain everything necessary for proper protection of materials and Works from any damage by weather.
C | Control of Workmen, Plant And Machinery At Site
The Contractor shall be responsible for controlling all persons under his employment and those employed by his sub-contractors, merchants and haulers at the work site and shall take all necessary precautions to prevent damage and nuisance of any kind and shall indemnify the Government against any claim arising therefrom.
The Contractor shall ensure, so far as is practicable, the safety, health and welfare at work of all his workmen including:
i) The provision and maintenance of plant and system of work that is safe and without risks to health;
ii) Ensuring safety and absence of risks to health in connection with the use or operation, handling, storage and transport of plant and substances;
iii) The provision for such information, instruction, training and supervision as is necessary to ensure the safety and health at work of his workmen;
The Contractor shall locate the actual position and provide support and full protection of existing services and mains during the progress of the Works. The Contractor shall inform the S.O. of all arrangements with the various authorities.
D | Temporary Diversion And Relocation Of Existing Overhead And Underground Services
The Contractor shall enquire from the various authorities and make arrangements for the disconnection, removal, relocation and reconnection of services and pay all necessary cost and fees in connection therewith and make good all damage as specified.
E | Temporary Water And Power Supplies For The Works
Temporary water and electrical supply obtained from UTM shall be approved and billed accordingly by the S.O. The Contractor to liaise with the UTM to take possession of and install all meters and connect all services including dismantling all temporary services upon completion.
TO COLLECTION

## LATEST
KERJA-KERJA PEMBAIKAN FIRE COMMAND CENTRE (FCC) DI KAMPUS UNIVERSITI TEKNOLOGI MALAYSIA, JOHOR BAHRU, JOHOR
PRELIMINARIES
ITEM | DESCRIPTION | AMOUNT (RM)
1 | PROJECT SIGNBOARD
Provide a new project signboard in Bahasa Melayu as per UTM’s drawing and approved by S.O. Adapt, extend, sign write from time to time as required by the S.O. within one (1) month after received Letter of Acceptance and pay all costs in connection for the duration of the contract period.
2 | TEMPORARY DIVERSION AND RELOCATION OF EXISTING OVERHEAD AND UNDERGROUND SERVICES
The Contractor shall enquire from the various authorities and make arrangements for the disconnection, removal, relocation and reconnection of services and pay all necessary cost and fees in connection therewith and make good all damage as specified.
3 | CONSTRUCTION PLAN
The Contractor shall submit to the S.O. for his approval the following as specified a) Programme of Works b) Method statements c) Contractor's organisation chart d) Schedules e) Quality Assurance Plan for Works Contract worth RM10 Million and above.
i) Provide a Quality Assurance Team full time on Site for the institution, administration and maintenance of the Quality Assurance Plan and the preparation and submission of all Quality Assurance Reports as specified, throughout the duration of the contract.
ii) The Contractor shall appoint a suitably qualified and experienced person to act solely as a Quality Assurance Officer full time on site to lead Quality Assurance Team. (Refer Addendum to specification for project worth RM 10 Million and above).
4 | CONTRACTOR'S PLANT
The Contractor shall provide, erect, keep insured, maintain and remove on completion all requisite scaffolding, hoist, cranage, construction plant, ladder, staging, tarpaulins, et cetera (excluding piling and pile testing equipment), as necessary for the execution of the Works.
5 | TEMPORARY WATER AND POWER SUPPLIES FOR THE WORKS
Temporary water and power including electrical supply obtained from UTM shall be approved and billed accordingly by the S.O. The Contractor to liaise with the UTM to take possession of and install all meters and connect all services including dismantling all temporary services upon completion.
6 | SITE SECURITY
The Contractor shall provide all necessary lighting for the security of the site at all times until completion of the whole Works as specified.
TO COLLECTION
PRELIMINARIES ITEM (Cont'd)
7 | TEMPORARY ACCESS AND MAINTENANCE OF EXISTING ROADS
The Contractor shall provide and maintain all necessary temporary roads, culverts, tracks, bridges, et cetera for access to and within the Site as specified.
The Contractor shall maintain all access including existing roads, bridges, drains, culverts, roadside furniture, and all other appurtenances and services on such roads throughout the construction period. The Contractor shall make good any above mentioned item damaged by any work carried out by him.
The Contractor shall locate the actual position and provide support and full protection of existing services and mains during the progress of the Works. The Contractor shall inform the S.O. of all arrangements with the various authorities.
8 | CONTROL OF WORKMEN, PLANT AND MACHINERY AT SITE
The Contractor shall be responsible for controlling all persons under his employment and those employed by his sub-contractors, merchants and haulers at the work site and shall take all necessary precautions to prevent damage and nuisance of any kind and shall indemnify the Government against any claim arising therefrom.
The Contractor shall ensure, so far as is practicable, the safety, health and welfare at work of all his workmen including:
i) The provision and maintenance of plant and system of work that is safe and without risks to health;
ii) Ensuring safety and absence of risks to health in connection with the use or operation, handling, storage and transport of plant and substances;
iii) The provision for such information, instruction, training and supervision as is necessary to ensure the safety and health at work of his workmen;
9 | CONTRACTOR'S OFFICE AND STORAGE
The Contractor shall provide and maintain his own temporary one (1) no of site office with size 20’ x 10’ within the site area during the construction period. The site office shall at least of portable cabin type and complete with an air conditioned room for meeting with S.O which can accommodate minimum 10 persons. The exact location proposed by the Contractor shall be subject to S.O’s approval. The Contractor shall provide and maintain all necessary electrical power supply, fitting, chair, table, magnetic white board, fire extinguisher and drawing rack (adequate for all drawing). On completion of the works and upon instruction by S.O after the issuance of Certificate of Practical Completion, the said site office shall be removed from the site immediately and all services related thereto to be disconnected to the approval of the S.O and relevant authority and the site shall be kept clean and tidy.
TO COLLECTION
PRELIMINARIES ITEM (Cont'd)
10 | CARE AND PROTECTION OF MATERIALS AND WORKS
The Contractor shall provide and maintain everything necessary for proper protection of materials and Works from any damage by weather.
11 | SHOP DRAWINGS, SAMPLES AND MOCK-UPS
The Contractor shall submit for approval relevant shop drawings as requested by the S.O. The Contractor shall submit samples of materials or execute samples of workmanship for the S.O.’s approval, and for further samples as required until the samples submitted or executed are in accordance with this Specification. The Contractor shall prepare sample installations as required to match specified works in all respects before proceeding with work. Mock-up units approved and accepted by the S.O. shall be referred as the standard of comparison for the work. The Contractor shall submit for approval as requested by the S.O., manufacturer's specifications, installation instruction, general recommendation for the work, including certified laboratory test reports and other data required to show compliance with these specifications.
12 | PROGRESS PHOTOGRAPHS
The Contractor shall prepare and submit to the S.O. within first week of every month four (4) copies of report on the progress of works at site. The report shall be by Section and/or Trades and to include the works of Sub-Contractors. It should also stated the number and deployment of workmen employed, materials and goods delivered, extent and type of plant used, site instruction, weather conditions, OSHE reports as required by the OSHA, visitors and other information relevant to the Works.
The Contractor shall take progress photographs of the works at monthly interval as directed by the S.O. The average number of different photographs to be taken shall be sufficient enough to show the progress of the work but in any case the average number per month shall not be less than four (4) postcard size coloured prints and each of the approved photographs submitted to the S.O all titled and dated.
13 | SURVEY INSTRUMENTS AND PERSONNEL
The Contractor shall provide all such instruments, equipment and survey personnel as specified throughout the duration of the original Contract Period until 6 months after the issuance of the Certificate of Practical completion as per SO required.
14 | SITE ITEMS FOR S.O./OFFICE EQUIPMENT AND FACILITIES
The Contractor shall provide all Personal Protective Equipment required for the use of the S.O. and his supervisory staff complete as specified and complying with DOSH requirements.
The Contractor shall provide suitable types of fire extinguishers as specified.
TO COLLECTION
PRELIMINARIES ITEM (Cont'd)
The Contractor shall provide the equipment and facilities as listed as specified in APPENDIX A/2 for the use of the S.O., his representatives and staff throughout the duration of the original Contract Period.
The Contractor shall provide suitable transportation service by means of vehicle(s) including licensed and competent driver(s) as specified in APPENDIX A/3 throughout the duration of the original Contract Period.
15 | SAFE WORKING AREA
The Contractor shall supply, erect, maintain and remove on completion of the Works, scaffolding and working platform with safety nettings, catch platforms, safety barricades, fencing, railing, screen wire netting and toe board, guardrails or board fences and sufficient illuminations, all as specified.
The Contractor shall supply, erect, maintain and remove on completion of the Works, adequate, protective and security hoarding, scaffolding and working platform with safety nettings and such other safety measures necessary to ensure the safety of the workers, personnel, public and others at or within the vicinity of the Site, all as specified.
For work in confined spaces, the Contractor shall;
i) Ensure that closed tanks with restricted means of entry and exit, open manholes, trenches, pipes, flues, ducts, ceiling voids, basements and other places where there is inadequate ventilation and/or the air is either contaminated or oxygen deficient, be tested before entry to determine that there are adequate levels of oxygen present, and that dangerous amounts of flammable and or poisonous gases are not present.
ii) Establish a safe work system and adopt entry permit system for workers who will be carrying out their work in confined spaces.
16 | SAFETY, HEALTH AND WELFARE
The Contractor shall ensure the safety, health and welfare at work site as specified including but not limited to : a) Provision of First Aid Kit b) Pest control including keeping the site clean and dry to prevent breeding of mosquitoes, rodents, insects and vermin of any kind. c) Fogging at regular intervals
The Contractor shall employ a Site Safety Supervisor (SSS) registered with DOSH to be stationed a minimum of 15 hours a week at the site for the entire duration of the construction period.
The Contractor shall submit 5 copies of Safety and Health Plan (S-Plan) as required in APPENDIX A/5 as specified.
TO COLLECTION
PRELIMINARIES ITEM (Cont'd)
The Contractor shall submit 5 copies of monthly Safety and Health Report as required in APPENDIX A/6 as specified.
The Contractor shall provide and maintain adequate traffic safety and control including signages, warning lights and flagmen as necessary.
17 | KEEPING THE SITE TIDY
The Contractor shall make every effort to keep the Site in a reasonably clean and tidy condition for the duration of the Works. He shall, in addition, from time to time and on the completion of any area of the Works or where directed by the S.O., remove rubbish, surplus materials, or any other construction debris from such areas as may be attributable to his work under this Contract and generally maintain the Site in a satisfactory condition, to the approval of the S.O.
The Contractor shall gather up and clear away all rubbish as it accumulates during the progress of the Works at least twice each week at times approved by the S.O. The services shall be continued until the completion of the Works. Garbage or construction waste shall be disposed in a locally available landfill or hauled to disposal sites approved by the S.O.
18 | AS-BUILT DRAWINGS
The Contractor shall provide for the S.O.’s office, four (4) sets of approved as-built drawings and operation & maintenance manuals related to the works within three month after completion of the works. The softcopy of as-built drawings must also be submitted in the CD format approved by the S.O. All hardcopy drawings shall be A1 size (838mm x 584mm) and binding with hardcover unless otherwise approved by the S.O. or his representative. The As-built drawing shall be endorsed by a Professional Architect/Engineer/Surveyor registered with the respective professional Board in Malaysia.
19 | CLEARING, CLEANING AND MAKING GOOD ON COMPLETION
The Contractor shall clear and clean the Works including existing roads, drains bounding the Site of any debris, earth, et cetera, and make good all damages upon completion as specified.
20 | WASTE MANAGEMENT
The Contractor shall be responsible for the cleaning of workplace area in every working day into temporary Roro tank provided by Contractor. The contractor(s) shall collect the construction waste, scheduled waste and domestic waste from the site to approve locations for disposal or to recycle the waste. Roro tank must be emptied when necessary and after completion of work outside campus allowed by UTM / Local Authorities. Roro tank must be removed from the construction site when the work is upon completion.
TO COLLECTION
PRELIMINARIES ITEM (Cont'd)
21 | UNIFORM
The Contractor shall ensure the workers wear the uniform at all time at the work site. The uniform for the workers shall follow design and colour code specified by the UTM. The uniform for the workers shall follow design and colour code specified by the UTM.
22 | SITE MEETING
Company’s director shall attend all site meetings as required by the S.O. together with the senior members of his staff and the Foreman in charge. Their presence is required to bring about the proper management and co-ordination of the Contract as well as to report the progress of the works and resolve any problems. The Contractor shall inform the Sub-Contractors and Suppliers when their presence at meetings are required and if necessary shall hold meetings with them prior to the main site meeting to facilitate accurate reporting of progress. Provide all necessary meeting requirement for site possession meeting, site meeting and technical meeting related to the Contract.
23 | FORM OF CONTRACT
The Contractor shall refer to the Standard Form of Contract for further information. The Contractor may price here for all the expenses involved in complying with the terms of these Clauses, otherwise such expenses are deemed to be included elsewhere.
24 | CLAUSE 13 - PERFORMANCE BOND
For due observance and performance of this contract the Contractor shall have to provide:
Performance Bond in the form of an approved Bank or Insurance Guarantee equal to five percent (5%) of the contract sum to be deposited with the Government as a condition precedent to the commencement of any work under this contract.
25 | CLAUSE 15 - INSURANCE AGAINST PERSONAL INJURIES AND DAMAGE TO PROPERTY
26 | CLAUSE 16 - INDEMNITIES TO GOVERNMENT IN RESPECT OF CLAIM BY WORKMEN
27 | CLAUSE 17 - EMPLOYEE'S SOCIAL SECURITY ACT, 1969
28 | CLAUSE 18 - INSURANCE OF WORKS.
29 | CLAUSE 22 - DESIGN, SUB-CLAUSE 22.2 DESIGN GUARANTEE BOND
30 | CLAUSE 35 - MATERIALS, GOODS AND WORKMANSHIP OPENING UP OF WORK FOR INSPECTION OR TESTING OF MATERIALS OR GOODS
TO COLLECTION
COLLECTION :
From Page No. PHT 1
From Page No. PHT 2
From Page No. PHT 3
From Page No. PHT 4
From Page No. PHT 5
From Page No. PHT 6
CARRIED FORWARD TO GENERAL SUMMARY

## PREAMBLES
KERJA-KERJA PEMBAIKAN FIRE COMMAND CENTRE (FCC) DI KAMPUS UNIVERSITI TEKNOLOGI MALAYSIA, JOHOR BAHRU, JOHOR
PREAMBLES
ITEM | DESCRIPTION
A | GENERAL INFORMATION TO BILL OF QUANTITIES
1 | GENERAL
1.1 | The Works contained in the Contract shall include the provision of all labour, materials, constructional plant, temporary or permanent works as required in the Contract.
1.2 | The Bill of Quantities shall be read in conjunction with the Conditions of Contract, the Specification and the Drawings in the Contract Documents.
1.3 | The items as set out in the Bill of Quantities shall apply to the whole of the Works contained in the Contract and the Contractor shall allow for compliance with the same and for any cost incurred in connection therewith.
1.4 | Headings are not comprehensive and do not necessarily reflect or modify the meaning of the items in the B.Q. The exact nature and extent of the work to be carried out shall be ascertained by reference to the Contract as a whole, in particular the Conditions of Contract, the Specification and the Drawings. It shall be read together with the relevant "Method of Payment".
1.5 | The amounts inserted by the Contractor for such items shall be deemed to apply to the whole of the Works carried out under this Contract.
1.6 | Each item shall be individually priced. Bulk pricing for sections, trades, groups or pages of items shall not be allowed and no subsequent claims for loss or expense and/or profit shall be entertained for failure to comply with this clause.
1.7 | The rates and prices inserted in the Bill of Quantities shall include cost of the works described, all risks, liabilities and obligations set forth or implied in the Contract Document and shall be deemed to include the following, unless expressly stated otherwise:
| (a) | the provision of labour and all costs in connection therewith;
| (b) | the supply of materials, goods, equipment and storage thereof including delivery to site and all costs in connection therewith;
| (c) | taking delivery of materials, goods and equipment necessary for the Works and including those supplied by others, loading and unloading, storage and all costs in connection therewith;
| (d) | the usage of plants and machineries and all costs in connection therewith;
| (e) | the fixing, erecting and installing or placing in position of materials, goods and equipment including around obstruction, tolerances, penetration, working space, over-breaks etc, and all costs in connection therewith;
| (f) | the provision of all temporary works and all costs in connection therewith unless separately provided for in the Bill of Quantities;
GENERAL INFORMATION TO BILL OF QUANTITIES (Cont'd)
| (g) | the phasing requirements of the Works including the effect on the programming of the Works of all traffic and drainage diversions, special structural requirements, earthwork restrictions, alterations to services and street lighting (executed under the Contract or in conjunction with it) and all other requirements of the Contract and all costs in connection therewith;
| (h) | all cost of testing to show proof of compliance with the Specification on materials and workmanship inclusive of samples of materials and submission of tests results. Should the frequency of testing and sampling not specified, then it shall be in accordance with the relevant Malaysian/British Standards and Codes of Practice, Where there is no such relevant Standards and Codes of Practice for reference, it shall then be as instructed by the S.O.;
| (i) | all royalties and dues which the Contractor may be required to pay;
| (j) | wastage;
| (k) | establishment charges, overheads and profit;
| (l) | whatsoever method of construction the Contractor may adopt.
1.8 | Where any priced item in the B.Q. but has not been executed on site by the Contractor, the cost of such priced item shall accordingly be deducted from the Contract Sum.
1.9 | All items priced shall be deemed to include compliance with the provisions of the contract, statutes, regulation, by-laws or any order or directive issued by public authority or public service company and other related legislation currently in force.
1.1 | Notwithstanding the above clauses, the S.O. reserves the right to request from the Contractor the detailed breakdown Of the pricing for items or rates in the B.Q. for his perusal. The detailed breakdown pricing may be used as a basis for the administration of the Contract
2 | MEASUREMENT
2.1 | Quantities in the Bills of Quantities are measured in accordance with the Malaysian Standard Method of Measurement of Building Works (2nd Edition Metric 2000). Where departure have been made from the standards mentioned, the method adopted in the Bills shall be adhered to for the purposes of ascertaining the value of all variations and measurements.
3 | UNPRICED ITEMS
3.1 | Where any item is left unpriced, it shall be deemed that the cost of such item has been allowed for elsewhere within this document. No subsequent claims arising out of expense and/or loss incurred against such unpriced item shall be entertained.
GENERAL INFORMATION TO BILL OF QUANTITIES (Cont'd)
4 | GENERAL ATTENDANCE FOR NOMINATED SUB-CONTRACTORS AND NOMINATED SUPPLIERS
4.1 | Attendance and facilities for Nominated Sub-contractors and nominated suppliers shall include:
| (a) | in the case of works or services executed : for allowing the use of existing working space, access, temporary roads, erected scaffolding, sanitary, welfare and other facilities existing on Site and the provision of protection, water, electricity for lighting and clearing away rubbish and debris arising from the work;
| (b) | in the case of goods, materials or services supplied: for taking delivery, unloading, storing, protection and returning crates, cartons and packing materials,
all as specified in the specification
5 | PHASING SEQUENCE OF OPERATIONS AND METHODS OF CONSTRUCTION
5.1 | The rates and prices shall, unless otherwise stated, include for the costs of compliance with any restrictions imposed on the programming of the Works by the Government and Local Authorities and other relevant authorities dealing with phasing sequence of operations, method of construction, safety and health and liaison and access.
6 | TRIALS, SAMPLES, TESTS AND INSPECTION
6.1 | The rates and prices shall include for a testing laboratory or an accredited laboratory approved by SIRIM, equipment and staff for carrying out the testSI tests and the effects on the progress of the Works for the carrying out of all trials, sampling and tests whether specified in the Contract Document or otherwise in order to ensure compliance with the requirements of the Specification except where separately itemised in the Bill of Quantities.
7 | EXISTING SERVICES AND MAINS
7.1 | The Contractor shall include in his rates and prices for taking measures to locate the actual position and provide support and full protection of existing services and mains and other equipment and machineries during the progress of the Works. The Contractor shall inform the SO. of all arrangements with all Statutory and Public Utility Authorities.
8 | WORK UNDER WATER
8.1 | The rates shall include any costs arising from and in connection with the execution of work under water wherever required unless otherwise stated.
9 | PHRASEOLOGY
9.1 | Differences in the method of billing and in phraseology used in various parts of the Bill of Quantities and/or Schedule of Rates shall not be a basis of any claim for an increase in the rates and prices.
GENERAL INFORMATION TO BILL OF QUANTITIES (Cont'd)
10 | PROVISIONAL SUMS
10.1 | All provisional sums included in the Bill of Quantities are intended to be approximate indications only of the amounts to be expended in respect of the work described and may be omitted entirely or substantially varied without entitling the Contractor to any claim for compensation. No part of the Contractor's overhead, expenses or profit should be included in these sums when the bill is priced unless items for profit and attendance are specifically allowed for.
11 | CURRENCY OF PAYMENT
11.1 | Pricing of the Contract shall be in Malaysian Ringgit to two decimal place. Payment to the Contractor under the Contract shall be in Malaysian Ringgit.
12 | TEMPORARY DIVERSIONS
Work in connection with the temporary diversion and relocation of existing overhead and underground services, whether detailed in the Contract or not shall be covered by the appropriate Lump Sum Items in Bill No. 1 : Preliminaries and General Conditions unless separately measured in other parts of the Bill of Quantities.
13 | ABBREVIATIONS
13.1 | The following abbreviations or symbols are generally used in the Contract Document and shall be read as follows:
| (a) | mm | : | milimetre
| (b) | m | : | metre
| (c) | m2 | : | square metre
| (d) | m3 | : | cubic metre
| (e) | kg | : | kilogramme
| (f) | tonne | : | metric ton
| (g) | No. | : | Number
| (h) | L.S. | : | Lump Sump
| (i) | P.C. Sum | : | Prime Cost Sum
| (j) | P.S. | : | Provisional Sum
| (k) | RM | : | Ringgit Malaysia
13.2 | The following abbreviations appearing in these Specifications have their meanings as assigned against them:
| (a) | B.Q. | : | Bills of Quantities
| (b) | CIAST | : | Pusat Latihan Pengajar dan Kemahiran Lanjutan
| (c) | CIDB | : | Construction Industry Development Board
| (d) | CoW | : | Clerk of Works
| (e) | DGFR | : | Director General of Fire and Rescue
| (f) | DOE | : | Department of Environment
| (g) | DOSH | : | Department of Occupational Safety and Health
| (h) | EMP | : | Environmental Management Plan
| (i) | JKR | : | Jabatan Kerja Raya
| (j) | MOH | : | Ministry of Health
| (k) | MSMA | : | Manual Saliran Mesra Alam
GENERAL INFORMATION TO BILL OF QUANTITIES (Cont'd)
| (l) | MTIB | : | Malaysian Timber Industry Board
| (m) | PDRM | : | Polis Diraja Malaysia
| (n) | P.E. | : | Professional Engineer
| (o) | R.O.W. | : | Right Of Way
| (p) | S.O. | : | Superintending Officer
| (q) | S.P. | : | System Provider
| (r) | SIRIM | : | Standards and Industrial Research Institute of Malaysia
| (s) | SPAN | : | Suruhanjaya Perkhidmatan Air Negara
14 | SCOPE OF WORKS
14.1 | The Works covered in this Contract comprise the provision by the Contractor at his own risk and cost of all materials, scaffolding, tools, plant, labour, transport, water, light and everything else necessary for the construction and completion of .......................................................................... …………………………………...............................................................................................................................................................................………………………….……all to the approval of the S.O.
14.2 | The Conditions of Contract for the Works, which is embodied in the Form of Contract (Form PWD 203 / Form PWD 203A), shall be read in conjunction with this Specification. A copy of the Form of Contract is available for inspection on the Tender Table on any working day up to the time appointed for receiving tenders. If the tenderer considers that any of the clauses of the Contract involves expenses, he shall allow for the money value of such clauses in his Tender.
15 | LOCATION OF SITE
The site for the proposed Works is located at …………………………………….…………………..
……………………………………………………………………………………………………………..
……………………………………………………………………………………………………………..
as shown on Drawing No ……………………………………………………………………………….
16 | CONTRACT DOCUMENTS
16.1 | The Contract Documents shall consist of:
| (a) | PWD Form of Contract (for contract based on Drawings and Specification or for contract based on Quantities);
| (b) | Form of Tender;
| (c) | Letter of Acceptance of Tender;
| (d) | Special Provisions to the Conditions of Contract as listed in the PWD Form of Contract;
| (e) | Contract Drawings;
| (f) | Specifications;
| (g) | Summary of Tender (for contract based on Quantities, this item is part of the B.Q.);
GENERAL INFORMATION TO BILL OF QUANTITIES (Cont'd)
| (h) | Schedule of Rates (for contract based on Drawings and Specifications) or B.Q. (for contract based on Quantities);
| (i) | Any other relevant documents included therein.
16.2 | The documents shall be taken as mutually explanatory of each other and in case of any discrepancy or inconsistency, the following rules shall apply:
| (a) | The Conditions of Contract (PWD Form 203/ PWD Form 203A) shall take preference over all other documents.
| (b) | Special Provisions to Conditions of Contract shall take preference over Conditions of Contract.
| (c) | In Drawings, large scale details shall take preference over small scale Drawings.
| (d) | The Addendum Specification shall take preference over the Standard Specifications and Drawings.
| (e) | Drawings shall take preference over Standard Specifications.
16.3 | Any discrepancies shall be referred as soon as possible to the S.O. who shall decide which shall be followed.
16.4 | The contractor shall solely bear the hard cover binding cost for five (5) copies of contract documents.
17 | USE OF LOCAL MATERIALS
17.1 | The Contractor shall use locally manufactured materials and goods as listed in the ‘Senarai Bahan/Barangan Binaan Buatan Tempatan’ issued by IKRAM QA Services Sdn. Bhd. and/or ‘Senarai Bahan/Barangan Buatan Tempatan’ issued by SIRIM QA Services Sdn. Bhd., whichever is relevant. If the Contractor fails to comply with this requirement, a penalty shall be imposed and/or the materials supplied shall be rejected.
17.2 | The locally manufactured materials and goods which are not listed aforesaid, may be permitted if the materials have been tested and certified by IKRAM QA Services Sdn. Bhd. or SIRIM QA Services Sdn. Bhd. whichever is relevant. If the testing cannot be carried out by IKRAM QA Services Sdn. Bhd. or SIRIM QA Services Sdn. Bhd., the Contractor may apply and, subject to the approval of the S.O., carry out the testing by other agencies.
17.3 | Under no circumstances will the Contractor be permitted to incorporate or supply imported materials, plant, equipment, or other goods into the Works or forming part of the scope of the Works except those approved by the Government, prior to the execution of the Contract. The Contractor shall substitute any materials, plant, equipment, or other goods proposed to be imported but not approved by the Government, with suitable local materials, plant, equipment, or other goods, including making any necessary sub-sequential changes or adjustments to the design of the Works to accommodate such substitution, all to the concurrence of the S.O.
GENERAL INFORMATION TO BILL OF QUANTITIES (Cont'd)
17.4 | The Contractor shall ensure that the procurement of approved imported materials, plant, equipment, or other goods are obtained directly from the country of origin based on Free On Board (F.O.B) or other similar basis. The transportation and insurance of such imported materials, plant, equipment, or other goods from the country of origin to the Site shall be arranged by the Contractor through approved Government’s Multi Modal Transport Operators (MTO). The Contractor shall allow in his tender all costs and time required in complying with the requirements of this clause including the cost required for the services provided by the MTO.
17.5 | The Contractor shall submit documentary evidence of compliance with this clause to the S.O. within one (1) month from the date of each delivery to the Site of such materials, plant, equipment, vehicles or other goods.
18 | ADJOINING PROPERTY
Where the property adjoining the Site is in constant use by the Employer/adjoining owners and occupiers, the Contractor shall arrange and carry out the Works so as to cause minimum interference or interruption to the use of adjoining properties including roads, footpaths, other access and any existing services thereto. He shall comply with all instructions or directions given by the S.O. in these matters.
19 | SUFFICIENT NOTICE TO LOCAL AUTHORITIES
19.1 | The Contractor shall give sufficient notice to the relevant Local Authorities/Utility Providers/Regulatory Bodies before commencing or to inspect any works in relation to their scope of services. Failure to give sufficient notice shall not entitle the Contractor to extension of time due to any subsequent delays in connection with the Works.
19.2 | Any notice given to the above mentioned authorities shall also be copied to the S.O.
20 | PARTICULAR OF EMPLOYEES
The Contractor shall on each working day furnish to the S.O., maintain and update a full list of all his workers including all workers employed by his sub-contractors or Nominated Subcontractors on the work site giving all particulars in the format as approved by the S.O.
21 | COORDINATION OF MECHANICAL AND ELECTRICAL SERVICES
21.1 | General
This section shall describe the scope of works, qualifications, competency, roles and responsibilities of the Mechanical and Electrical (M & E) Services Coordination Team.
21.2 | Scope Of Work
| (a) | The Contractor shall be responsible for coordinating the implementation of all M & E works and related activities within the project scope. For this purpose the Contractor shall appoint M & E Services Coordinators full time on site during the whole duration of the works. The appointment shall be approved by the S.O.
GENERAL INFORMATION TO BILL OF QUANTITIES (Cont'd)
| (b) | The Contractor shall ensure all M & E requirements are implemented in a timely manner and adequately integrated with all services involved such as architectural, structural and other related services.
| (c) | The Contractor shall conduct regular coordination meetings among all sub-contractors, nominated or otherwise, from related disciplines to evaluate and resolve all issues or problems regarding integration and coordination of all services.
21.3 | Minimum Requirement Of M & E Services Coordinator Based On Project Cost As Followed:
|  | Project Cost (RM) |  |  | Minimum Requirement Of M & E Coordinator
|  | between 10 to 50 million |  |  | 1 Engineer & 1 CoW
|  | more than 50 million |  |  | 1 Engineer & 2 CoW
21.4 | Qualification And Competency Of M & E Coordinators
| (a) | Engineer
Degree in related engineering field with minimum three (3) years of working experience in building construction.
| (b) | Clerk of Works (CoW)
Diploma in related engineering field with minimum five (5) years of working experience in building construction.
21.5 | Responsibilities Of M & E Services Coordinator
| (a) | The M & E Services Coordinator shall be responsible, on behalf of the Contractor for :
|  | (i) | Guiding the overall M & E works and implementation of related activities within the project scope and providing timely and relevant information.
|  | (ii) | Ensuring that all layout, schematic, detail and Builder’s Work in Connection (BWIC) drawings (for architectural, structural, mechanical and electrical works) are received from the S.O.
|  | (iii) | Supervising all the installation and construction works to ensure the works are sufficiently coordinated.
|  | (iv) | Identifying and resolving issues or problems related to integration and coordination of services by producing coordinated services drawing, new method of installation and et cetera.
GENERAL INFORMATION TO BILL OF QUANTITIES (Cont'd)
22 | PERFORMANCE WARRANTY
The Contractor shall submit to the S.O. the performance warranty of (manufacture's and workmanship works warranty) for list item (if accordingly) and other items as specified in the Guideline and/or specifications.
| (a) | Anti - termite |  | - 3 years
| (b) | Waterproofing |  | - 3 years
| (c) | Painting |  | - 5 years
| (d) | Metal Deck |  | - 25 years
| (e) | Others |  | - (Please specified)